## Sheet1
No | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | + | +
No | 조직 | 공장 | 생산 라인 | W/O | 모델 | Suffix | 부품번호 | 혼류 | Lot Code | New Model | New Model | Event | Setting | ECO Level | 고객사 | Customer Code | Planned Start Time | Planned End Time | Plan Due Date | Production Start Date | Production End Date | Week | FromSeq | ToSeq | Delay | S/T (min) | BuyerModel | Fix | BOM | 라벨 | EANCODE | PR | 비고 | Manager Remark | 수량 | 수량 | 수량 | Model ECO | Not in 6 Months | 2월 | 2월 | 2월 | 3월 | 3월 | 3월 | 3월 | 3월
No | 조직 | 공장 | 생산 라인 | W/O | 모델 | Suffix | 부품번호 | 혼류 | Lot Code | New Model | New Model | Event | Setting | ECO Level | 고객사 | Customer Code | Planned Start Time | Planned End Time | Plan Due Date | Production Start Date | Production End Date | Week | FromSeq | ToSeq | Delay | S/T (min) | BuyerModel | Fix | BOM | 라벨 | EANCODE | PR | 비고 | Manager Remark | W/O 계획수량 | W/O Input | W/O실적 | Model ECO | Not in 6 Months | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5
|  | Sum | [32 empty] | 8170 | 0 | 0 |  |  | 1160 | 1126 | 920 | 0 | 874 | 1160 | 1160 | 1160
1 | CVZ | Final Assembly | C11 | 6B1X00NM | LTGL6937F | AR1ELGA | LTGL6937F.AR1ELGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-25 18:28 | 2026-02-26 08:03 | 2026-02-10 | 2026-02-25 |  | 9 | 179 | 180 | -14 | 25.5953 | LTGL6937F |  | Y | N | 048231344173 | Y | 2/25(수)이후 가능(JAVA valve Vessel 지연) |  | 126 |  |  |  |  | 26: 7
2 | CVZ | Final Assembly | C11 | 6B1X00SV | LRIN6323YE | ASTLLCA | LRIN6323YE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 08:03 | 2026-02-26 09:12 | 2026-02-24 |  |  | 9 | 181 | 182 | 0 | 16.113 | LRIN6323YE |  | Y | N | 048231349642 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 137 |  |  |  |  | 26: 137
3 | CVZ | Final Assembly | C11 | 6B1X00SW | LRIN6323YE | ASTLLCA | LRIN6323YE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 09:12 | 2026-02-26 10:43 | 2026-02-24 |  |  | 9 | 183 | 184 | 0 | 16.113 | LRIN6323YE |  | Y | N | 048231349642 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 162 |  |  |  |  | 26: 162
4 | CVZ | Final Assembly | C11 | 6B1X00RJ | LREL6321S | ASTLLCA | LREL6321S.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 10:43 | 2026-02-26 13:49 | 2026-02-24 |  |  | 9 | 185 | 186 | 0 | 13.3229 | LREL6321S |  | Y | N | 048231341417 | Y | 2/23일 이후 변경(실란트 부족) |  | 252 |  |  |  |  | 26: 252
5 | CVZ | Final Assembly | C11 | 6B1X00T2 | LSIS6338NE | AEHLSTC | LSIS6338NE.AEHLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 13:49 | 2026-02-26 14:20 | 2026-02-24 |  |  | 9 | 187 | 188 | 0 | 17.8073 | LSIS6338NE |  | Y | N | 195174084427 | Y | 0.0 |  | 63 |  |  |  |  | 26: 63
6 | CVZ | Final Assembly | C11 | 6B1X00T1 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 14:20 | 2026-02-26 14:39 | 2026-02-24 |  |  | 9 | 189 | 190 | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 38 |  |  |  |  | 26: 38
7 | CVZ | Final Assembly | C11 | 6B1X00RN | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 14:39 | 2026-02-26 15:10 | 2026-02-24 |  |  | 9 | 191 | 192 | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 42 |  |  |  |  | 26: 42
8 | CVZ | Final Assembly | C11 | 6B1X00T0 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 15:10 | 2026-02-26 16:09 | 2026-02-24 |  |  | 9 | 193 | 194 | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 117 |  |  |  |  | 26: 117
9 | CVZ | Final Assembly | C11 | 6B1X00SX | LSES6338F | ARSLSTC | LSES6338F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 16:09 | 2026-02-26 16:13 | 2026-02-24 |  |  | 9 | 195 | 196 | 0 | 16.5455 | LSES6338F |  | Y | N | 195174035528 | Y | 0.0 |  | 9 |  |  |  |  | 26: 9
10 | CVZ | Final Assembly | C11 | 6B1X00RL | LSES6338F | ARSLSTC | LSES6338F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 16:13 | 2026-02-26 16:33 | 2026-02-24 |  |  | 9 | 197 | 198 | 0 | 16.5455 | LSES6338F |  | Y | N | 195174035528 | Y | 0.0 |  | 40 |  |  |  |  | 26: 40
11 | CVZ | Final Assembly | C11 | 6B1X00U1 | WDEP9427F | ARSLLGA | WDEP9427F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-26 16:33 | 2026-02-26 16:49 | 2026-02-24 |  |  | 9 | 199 | 200 | 0 | 42.0463 | WDEP9427F |  | Y | N | 048231344289 | Y | 0.0 |  | 32 |  |  |  |  | 26: 32
12 | CVZ | Final Assembly | C11 | 6B1X00UW | WDEP9427F | ARSLLGA | WDEP9427F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-02-26 16:49 | 2026-02-26 17:41 | 2026-02-24 |  |  | 9 | 201 | 202 | 0 | 42.0463 | WDEP9427F |  | Y | N | 048231344289 | Y | 0.0 |  | 43 |  |  |  |  | 26: 43
13 | CVZ | Final Assembly | C11 | 6B1X00TX | WDEP9423D | ABDLLGA | WDEP9423D.ABDLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-26 17:41 | 2026-02-26 17:48 | 2026-02-24 |  |  | 9 | 203 | 204 | 0 | 40.2495 | WDEP9423D |  | Y | N | 048231344807 | Y | 0.0 |  | 15 |  |  |  |  | 26: 15
14 | CVZ | Final Assembly | C11 | 6B1X00UV | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-02-26 17:48 | 2026-02-26 18:50 | 2026-02-24 |  |  | 9 | 205 | 206 | 0 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 123 |  |  |  |  | 26: 123
15 | CVZ | Final Assembly | C11 | 6B1X00TG | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | FO |  |  | LGEUS LOCATION OFL | USSE000046 | 2026-02-26 18:50 | 2026-02-26 18:51 | 2026-02-24 |  |  | 9 | 207 | 208 | 0 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y | 0.0 |  | 3 |  |  |  |  | 26: 3
16 | CVZ | Final Assembly | C11 | 6B1X00TK | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-02-26 18:51 | 2026-02-26 18:53 | 2026-02-24 |  |  | 9 | 209 | 210 | 0 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y | 0.0 |  | 3 |  |  |  |  | 26: 3
17 | CVZ | Final Assembly | C11 | 6C1X01WY | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-02-26 18:53 | 2026-02-26 18:54 | 2026-03-02 |  |  | 9 | 211 | 212 | 6 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y | 0.0 |  | 3 |  |  |  |  | 26: 3
18 | CVZ | Final Assembly | C11 | 6B1X00TJ | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-02-26 18:54 | 2026-02-26 18:56 | 2026-02-24 |  |  | 9 | 213 | 214 | 0 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y | 0.0 |  | 4 |  |  |  |  | 26: 4
19 | CVZ | Final Assembly | C11 | 6B1X00TH | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-26 18:56 | 2026-02-26 19:00 | 2026-02-24 |  |  | 9 | 215 | 216 | 0 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y | 0.0 |  | 7 |  |  |  |  | 26: 7
20 | CVZ | Final Assembly | C11 | 6B1X00YN | WCES6428F | ARSLSTC | WCES6428F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 19:00 | 2026-02-26 19:05 | 2026-02-24 |  |  | 9 | 217 | 218 | 0 | 21.3853 | WCES6428F |  | Y | N | 195174022863 | Y | 0.0 |  | 10 |  |  |  |  | 26: 10
21 | CVZ | Final Assembly | C11 | 6B1X00Z0 | WCES6428F | ARSLSTC | WCES6428F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-26 19:05 | 2026-02-26 19:10 | 2026-02-24 |  |  | 9 | 219 | 220 | 0 | 21.3853 | WCES6428F |  | Y | N | 195174022863 | Y | 3월변경(MWO 부족) |  | 10 |  |  |  |  | 26: 10
22 | CVZ | Final Assembly | C11 | 6C1X02LZ | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | M&M ELECTRONICS, S.A. | PA203091A2 | 2026-02-26 19:10 | 2026-02-26 19:17 | 2026-03-02 |  |  | 9 | 221 | 222 | 6 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 파나마 직선적 |  | 15 |  |  |  |  | 26: 15
23 | CVZ | Final Assembly | C11 | 6C1X02EE | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-26 19:17 | 2026-02-27 08:26 | 2026-03-03 |  |  | 9 | 223 | 224 | 7 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 76 |  |  |  |  | 26: 25; 27: 51
24 | CVZ | Final Assembly | C11 | 6C1X02DU | WCEP6423D | ABDLLGA | WCEP6423D.ABDLLGA |  |  |  |  | FO |  |  | M&M ELECTRONICS, S.A. | PA203091A2 | 2026-02-27 08:26 | 2026-02-27 08:36 | 2026-03-02 |  |  | 9 | 225 | 226 | 6 | 19.7255 | WCEP6423D |  | Y | N | 048231345323 | Y | 파나마 직선적 |  | 20 |  |  |  |  | 27: 20
25 | CVZ | Final Assembly | C11 | 6C1X02S8 | WSED7665B | AK1QEUR | WSED7665B.AK1QEUR |  |  | Y |  | FO |  |  | LGEES | ES001013A1 | 2026-02-27 08:36 | 2026-02-27 09:02 | 2026-03-05 |  |  | 9 | 227 | 228 | 9 | 16.5207 | WSED7665B |  | Y | Y | 8806091858085 | Y | 0.0 |  | 50 |  |  |  |  | 27: 50
26 | CVZ | Final Assembly | C11 | 6C1X02M1 | WSED3023B | ABKLLNA | WSED3023B.ABKLLNA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-02-27 09:02 | 2026-02-27 09:05 | 2026-03-03 |  |  | 9 | 229 | 230 | 7 | 15.6353 | WSED3023B |  | Y | Y | 195174071458 | Y | 0.0 |  | 5 |  |  |  |  | 27: 5
27 | CVZ | Final Assembly | C11 | 6C1X02AH | WS7D7631WB | ABKQEUN | WS7D7631WB.ABKQEUN |  |  |  |  | FO |  |  | LGESW | SE001021A1 | 2026-02-27 09:05 | 2026-02-27 09:37 | 2026-03-05 |  |  | 9 | 231 | 232 | 9 | 14.9435 | WS7D7631WB |  | Y | Y | 8806096444931 | Y | 0.0 |  | 62 |  |  |  |  | 27: 62
28 | CVZ | Final Assembly | C11 | 6C1X02AJ | WS7D7631WB | ABKQEUR | WS7D7631WB.ABKQEUR |  |  |  |  | FO |  |  | LGEES | ES001013A1 | 2026-02-27 09:37 | 2026-02-27 10:12 | 2026-03-05 |  |  | 9 | 233 | 234 | 9 | 14.9284 | WS7D7631WB |  | Y | Y | 8806096156421 | Y | 0.0 |  | 50 |  |  |  |  | 27: 50
29 | CVZ | Final Assembly | C11 | 6C1X02A2 | WS7D7632WB | ABKQEUN | WS7D7632WB.ABKQEUN |  |  |  |  | FO |  |  | LGESW | SE001021A1 | 2026-02-27 10:12 | 2026-02-27 10:43 | 2026-03-05 |  |  | 9 | 235 | 236 | 9 | 14.9435 | WS7D7632WB |  | Y | Y | 8806096444924 | Y | 0.0 |  | 60 |  |  |  |  | 27: 60
30 | CVZ | Final Assembly | C11 | 6C1X02PN | WS7D7632WB | ABKQEUN | WS7D7632WB.ABKQEUN |  |  |  |  | FO |  |  | NSI Electronic Aps/ DD | DK001741A1 | 2026-02-27 10:43 | 2026-02-27 11:39 | 2026-03-09 |  |  | 9 | 237 | 238 | 13 | 14.9435 | WS7D7632WB |  | Y | Y | 8806096444924 | Y | 0.0 |  | 108 |  |  |  |  | 27: 108
31 | CVZ | Final Assembly | C11 | 6C1X02A3 | WS7D7632WB | ABKQEUR | WS7D7632WB.ABKQEUR |  |  |  |  | FO |  |  | LGEES | ES001013A1 | 2026-02-27 11:39 | 2026-02-27 11:49 | 2026-03-05 |  |  | 9 | 239 | 240 | 9 | 14.9284 | WS7D7632WB |  | Y | Y | 8806096156391 | Y | 0.0 |  | 20 |  |  |  |  | 27: 20
32 | CVZ | Final Assembly | C11 | 6C1X02KU | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | M&M ELECTRONICS, S.A. | PA203091A2 | 2026-02-27 11:49 | 2026-02-27 13:10 | 2026-03-02 |  |  | 9 | 241 | 242 | 6 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 파나마 직선적 |  | 40 |  |  |  |  | 27: 40
33 | CVZ | Final Assembly | C11 | 6B1X00N9 | LSEL6335FE | AR1LLGA | LSEL6335FE.AR1LLGA |  |  |  |  | FO |  |  | LOWE'S COMPANIES, INC. | US044868A4 | 2026-02-27 13:10 | 2026-02-27 13:18 | 2026-02-06 |  |  | 9 | 243 | 244 | -18 | 14.0343 | LSEL6335FE |  | Y | N | 048231347396 | Y | 2/27일 변경(Harness vessel 지연),2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 16 |  |  |  |  | 27: 16
34 | CVZ | Final Assembly | C11 | 6B1X00RG | LSIL6332FE | ARSLLGA | LSIL6332FE.ARSLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-27 13:18 | 2026-02-27 13:22 | 2026-02-10 |  |  | 9 | 245 | 246 | -14 | 15.2146 | LSIL6332FE |  | Y | N | 048231347495 | Y | 2/27일 변경(Harness vessel 지연),2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 8 |  |  |  |  | 27: 8
35 | CVZ | Final Assembly | C11 | 6B1X00L4 | LSEL6335FE | AR1LLGA | LSEL6335FE.AR1LLGA |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-02-27 13:22 | 2026-02-27 14:06 | 2026-02-05 |  |  | 9 | 247 | 248 | -19 | 14.0343 | LSEL6335FE |  | Y | N | 048231347396 | Y | 2/27변경(Harness vessel 지연)2/23일 이후 변경,실란트 부족(미국향전기2.7천대),2/13아후 변경(멕시코 CKD 긴급 대응으로 인한 T/plate glass 부족) |  | 84 |  |  |  |  | 27: 84
36 | CVZ | Final Assembly | C11 | 6B1X00M3 | LSEL6335FE | AR1LLGA | LSEL6335FE.AR1LLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-02-27 14:06 | 2026-02-27 15:42 | 2026-02-06 |  |  | 9 | 249 | 250 | -18 | 14.0343 | LSEL6335FE |  | Y | N | 048231347396 | Y | 2/27변경(Harness vessel 지연)2/23일 이후 변경,실란트 부족(미국향전기2.7천대),2/13아후 변경(멕시코 CKD 긴급 대응으로 인한 T/plate glass 부족) |  | 168 |  |  |  |  | 27: 168
37 | CVZ | Final Assembly | C11 | 6B1X00WN | LSIU6339XE | ARSLLGA | LSIU6339XE.ARSLLGA |  |  | Y |  | FO |  |  | CFN | USSE000052 | 2026-02-27 15:42 | 2026-02-27 16:34 | 2026-02-24 |  |  | 9 | 251 | 252 | 0 | 0 | LSIU6339XE |  | Y | N | 048231349666 | Y | 2/27일 변경(개발지연) 2/24일 변경LG signiture 2세대 W10 선적 마지노선 |  | 100 |  |  |  |  | 27: 100
38 | CVZ | Final Assembly | C11 | 6C1X0228 | LSEL6331F | ARSLLCA | LSEL6331F.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-27 16:34 | 2026-02-27 17:31 | 2026-03-10 |  |  | 9 | 253 | 254 | 14 | 14.1608 | LSEL6331F |  | Y | N | 048231342025 | Y | 3/5일 계획, 2/27일 당김/장기 재고 소진을 위한 당김 생산 요청 |  | 52 |  |  |  |  | 27: 52
39 | CVZ | Final Assembly | C11 | 6C1X02D9 | LSEL6331F | ARSLLCA | LSEL6331F.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-27 17:31 | 2026-02-27 18:14 | 2026-03-10 |  |  | 9 | 255 | 256 | 14 | 14.1608 | LSEL6331F |  | Y | N | 048231342025 | Y | 3/5일 계획, 2/27일 당김/장기 재고 소진을 위한 당김 생산 요청 |  | 84 |  |  |  |  | 27: 84
40 | CVZ | Final Assembly | C11 | 6C1X02EA | LSEL6331F | ARSLLCA | LSEL6331F.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-27 18:14 | 2026-02-27 19:14 | 2026-03-10 |  |  | 9 | 257 | 258 | 14 | 14.1608 | LSEL6331F |  | Y | N | 048231342025 | Y | 3/5일 계획, 2/27일 당김/장기 재고 소진을 위한 당김 생산 요청 |  | 116 |  |  |  |  | 27: 116
41 | CVZ | Final Assembly | C11 | 6A1X15EY | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-27 19:14 | 2026-02-27 19:18 | 2026-01-30 |  |  | 9 | 259 | 260 | -25 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대),2/13이후 변경(Door glass vessel 지연) |  | 9 |  |  |  |  | 27: 9
42 | CVZ | Final Assembly | C11 | 6A1X15F0 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-27 19:18 | 2026-02-28 08:02 | 2026-02-09 |  |  | 9 | 261 | 262 | -15 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대),2/13이후 변경(Door glass vessel 지연) |  | 26 |  |  |  |  | 27: 23; 28: 3
43 | CVZ | Final Assembly | C11 | 6C1X02SF | WS9D7673CB | AK1QEUR | WS9D7673CB.AK1QEUR |  |  | Y |  | FO |  |  | LGEFS | FR001044A1 | 2026-02-28 08:02 | 2026-02-28 09:50 | 2026-03-05 |  |  | 9 |  |  | 9 | 0 | WS9D7673CB |  | Y | Y | 8806084888730 | Y | 0.0 |  | 216 |  |  |  |  | 28: 216
44 | CVZ | Final Assembly | C11 | 6B1X0091 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-28 09:50 | 2026-02-28 09:51 | 2026-02-06 |  |  | 9 |  |  | -18 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대),2/13이후 변경(Door glass vessel 지연) |  | 3 |  |  |  |  | 28: 3
45 | CVZ | Final Assembly | C11 | 6B1X00A5 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-28 09:51 | 2026-02-28 10:12 | 2026-02-10 |  |  | 9 |  |  | -14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 21 |  |  |  |  | 28: 21
46 | CVZ | Final Assembly | C11 | 6B1X00T4 | LDEL7324SE | ASTLLCA | LDEL7324SE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 10:12 | 2026-02-28 10:42 | 2026-02-24 |  |  | 9 |  |  | 0 | 20.7723 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 60 |  |  |  |  | 28: 60
47 | CVZ | Final Assembly | C11 | 6B1X00RH | LDEL7324SE | ASTLLCA | LDEL7324SE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 10:42 | 2026-02-28 11:22 | 2026-02-24 |  |  | 9 |  |  | 0 | 20.7723 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 80 |  |  |  |  | 28: 80
48 | CVZ | Final Assembly | C11 | 6B1X00ED | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-28 11:22 | 2026-02-28 11:23 | 2026-02-20 |  |  | 9 |  |  | -4 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 2 |  |  |  |  | 28: 2
49 | CVZ | Final Assembly | C11 | 6B1X00RD | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-02-28 11:23 | 2026-02-28 11:35 | 2026-02-27 |  |  | 9 |  |  | 3 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 24 |  |  |  |  | 28: 24
50 | CVZ | Final Assembly | C11 | 6B1X00YW | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-02-28 11:35 | 2026-02-28 11:50 | 2026-02-24 |  |  | 9 |  |  | 0 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 30 |  |  |  |  | 28: 30
51 | CVZ | Final Assembly | C11 | 6C1X026B | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-02-28 11:50 | 2026-02-28 13:32 | 2026-03-02 |  |  | 9 |  |  | 6 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 85 |  |  |  |  | 28: 85
52 | CVZ | Final Assembly | C11 | 6B1X00X8 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 13:32 | 2026-02-28 14:14 | 2026-02-24 |  |  | 9 |  |  | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 84 |  |  |  |  | 28: 84
53 | CVZ | Final Assembly | C11 | 6B1X00X6 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 14:14 | 2026-02-28 14:32 | 2026-02-24 |  |  | 9 |  |  | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 36 |  |  |  |  | 28: 36
54 | CVZ | Final Assembly | C11 | 6B1X00X7 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 14:32 | 2026-02-28 14:39 | 2026-02-24 |  |  | 9 |  |  | 0 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 13 |  |  |  |  | 28: 13
55 | CVZ | Final Assembly | C11 | 6B1X00X5 | LSGS6338F | ARSESTC | LSGS6338F.ARSESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 14:39 | 2026-02-28 14:44 | 2026-02-24 |  |  | 9 |  |  | 0 | 20.9165 | LSGS6338F |  | Y | N | 195174035535 | Y | 0.0 |  | 10 |  |  |  |  | 28: 10
56 | CVZ | Final Assembly | C11 | 6B1X00T6 | LREL6321S | ASTLLCA | LREL6321S.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-02-28 14:44 | 2026-03-02 08:13 | 2026-02-24 |  |  | 10 |  |  | 0 | 13.3229 | LREL6321S |  | Y | N | 048231341417 | Y | 2/23일 이후 변경(실란트 부족) |  | 278 |  |  |  |  | 28: 253; 2: 25
57 | CVZ | Final Assembly | C11 | 6CSYV006 | WCEP6423D | ABDLLGA | WCEP6423D.ABDLLGA |  |  |  |  | SY |  |  | LGEUS | US000491A1 | 2026-03-02 08:13 | 2026-03-02 08:18 | 2026-03-24 |  |  | 10 |  |  | 28 | 19.7255 | WCEP6423D |  | Y | N | 048231345323 | Y | 자재장기재고 도래,2월 생산필요 |  | 8 |  |  |  |  | 2: 8
58 | CVZ | Final Assembly | C11 | 6CSYV004 | WCEK6419S | ASTLSGN | WCEK6419S.ASTLSGN |  |  |  |  | SY |  |  | LGEUS | US000491A1 | 2026-03-02 08:18 | 2026-03-02 08:33 | 2026-03-24 |  |  | 10 |  |  | 28 | 21.0215 | SKSCV3002S |  | Y | N | 048231341295 | Y | 자재장기재고 도래,2월 생산필요 |  | 30 |  |  |  |  | 2: 30
59 | CVZ | Final Assembly | C11 | 6CSYV007 | WCES6428F | ARSLSTD | WCES6428F.ARSLSTD |  |  |  |  | SY |  |  | LGEUS | US000491A1 | 2026-03-02 08:33 | 2026-03-02 09:00 | 2026-03-24 |  |  | 10 |  |  | 28 | 21.512 | WCES6428F |  | Y | N | 195174024133 | Y | 자재장기재고 도래,2월 생산필요 |  | 50 |  |  |  |  | 2: 50
60 | CVZ | Final Assembly | C11 | 6CSYV005 | WCES6428N | AEHLSTD | WCES6428N.AEHLSTD |  |  |  |  | SY |  |  | LGEUS | US000491A1 | 2026-03-02 09:00 | 2026-03-02 09:42 | 2026-03-24 |  |  | 10 |  |  | 28 | 21.5887 | WCES6428N |  | Y | N | 195174070079 | Y | 자재장기재고 도래,2월 생산필요 |  | 80 |  |  |  |  | 2: 80
61 | CVZ | Final Assembly | C11 | 6B1X00RK | LRIN6323YE | ASTLLCA | LRIN6323YE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 09:42 | 2026-03-02 11:20 | 2026-02-24 |  |  | 10 |  |  | 0 | 16.113 | LRIN6323YE |  | Y | N | 048231349642 | Y | 3/2일 대응가능(S/heater 부족)2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 168 |  |  |  |  | 2: 168
62 | CVZ | Final Assembly | C11 | 6B1X00UH | LRIN6323YE | ASTLLGA | LRIN6323YE.ASTLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION OFL | USSE000046 | 2026-03-02 11:20 | 2026-03-02 11:42 | 2026-02-24 |  |  | 10 |  |  | 0 | 15.3337 | LRIN6323YE |  | Y | N | 048231349642 | Y | 3/2일 대응가능(S/heater 부족)2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 42 |  |  |  |  | 2: 42
63 | CVZ | Final Assembly | C11 | 6B1X00UF | LRIN6323YE | ASTLLGA | LRIN6323YE.ASTLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-02 11:42 | 2026-03-02 13:04 | 2026-02-24 |  |  | 10 |  |  | 0 | 15.3337 | LRIN6323YE |  | Y | N | 048231349642 | Y | 3/2일 대응가능(S/heater 부족)2/23일 이후 변경,실란트 부족(미국향전기2.7천대)2/7일변경(CKD공급으로 인한 변경)2/5일 변경 요청(멕시코 CKD 긴급 대응)Harness 2/2(월) 입항 예정으로 변경 |  | 42 |  |  |  |  | 2: 42
64 | CVZ | Final Assembly | C11 | 6B1X00UG | LRIN6323YE | ASTLLGA | LRIN6323YE.ASTLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-02 13:04 | 2026-03-02 13:29 | 2026-02-24 |  |  | 10 |  |  | 0 | 15.3337 | LRIN6323YE |  | Y | N | 048231349642 | Y | 3/2일 대응가능(S/heater 부족)2/23일 이후 변경,실란트 부족(미국향전기2.7천대) |  | 47 |  |  |  |  | 2: 47
65 | CVZ | Final Assembly | C11 | 6B1X00T5 | LREL6321S | ASTLLCA | LREL6321S.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 13:29 | 2026-03-02 14:59 | 2026-02-24 |  |  | 10 |  |  | 0 | 13.3229 | LREL6321S |  | Y | N | 048231341417 | Y | 3/2일 대응가능(S/heater 부족)2/23일 이후 변경(실란트 부족) |  | 170 |  |  |  |  | 2: 170
66 | CVZ | Final Assembly | C11 | 6C1X0294 | LSIS6338NE | AEHLSTC | LSIS6338NE.AEHLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 14:59 | 2026-03-02 15:21 | 2026-03-10 |  |  | 10 |  |  | 14 | 17.8073 | LSIS6338NE |  | Y | N | 195174084427 | Y | 0.0 |  | 24 |  |  |  |  | 2: 24
67 | CVZ | Final Assembly | C11 | 6C1X01L8 | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 15:21 | 2026-03-02 15:40 | 2026-03-10 |  |  | 10 |  |  | 14 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 35 |  |  |  |  | 2: 35
68 | CVZ | Final Assembly | C11 | 6C1X02D6 | LDEL7324SE | ASTLLCA | LDEL7324SE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 15:40 | 2026-03-02 15:42 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.7723 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 5 |  |  |  |  | 2: 5
69 | CVZ | Final Assembly | C11 | 6C1X022X | LDEL7324SE | ASTLLCA | LDEL7324SE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-02 15:42 | 2026-03-02 16:03 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.7723 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 40 |  |  |  |  | 2: 40
70 | CVZ | Final Assembly | C11 | 6C1X02MH | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-02 16:03 | 2026-03-02 16:13 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 18 |  |  |  |  | 2: 18
71 | CVZ | Final Assembly | C11 | 6C1X02MG | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-02 16:13 | 2026-03-02 16:35 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 42 |  |  |  |  | 2: 42
72 | CVZ | Final Assembly | C11 | 6C1X02DQ | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-02 16:35 | 2026-03-02 16:57 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 42 |  |  |  |  | 2: 42
73 | CVZ | Final Assembly | C11 | 6C1X02D7 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-02 16:57 | 2026-03-03 08:18 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 42 |  |  |  |  | 2: 6; 3: 36
74 | CVZ | Final Assembly | C11 | 6C1X023G | LSGS6338F | ARSESTC | LSGS6338F.ARSESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 08:18 | 2026-03-03 08:23 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.9165 | LSGS6338F |  | Y | N | 195174035535 | Y | 0.0 |  | 10 |  |  |  |  | 3: 10
75 | CVZ | Final Assembly | C11 | 6C1X02EC | LSGS6338F | ARSESTD | LSGS6338F.ARSESTD |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 08:23 | 2026-03-03 08:32 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.9165 | LSGS6338F |  | Y | N | 195174020722 | Y | 0.0 |  | 17 |  |  |  |  | 3: 17
76 | CVZ | Final Assembly | C11 | 6C1X02DT | LSGL6335X | ARSELCA | LSGL6335X.ARSELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 08:32 | 2026-03-03 08:47 | 2026-03-03 |  |  | 10 |  |  | 7 | 19.4038 | LSGL6335X |  | Y | N | 048231348942 | Y | 0.0 |  | 30 |  |  |  |  | 3: 30
77 | CVZ | Final Assembly | C11 | 6C1X023D | LSGL6335X | ARSELCA | LSGL6335X.ARSELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 08:47 | 2026-03-03 11:02 | 2026-03-03 |  |  | 10 |  |  | 7 | 19.4038 | LSGL6335X |  | Y | N | 048231348942 | Y | 0.0 |  | 250 |  |  |  |  | 3: 250
78 | CVZ | Final Assembly | C11 | 6C1X023E | LSGL6335Z | ABDELCA | LSGL6335Z.ABDELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 11:02 | 2026-03-03 11:22 | 2026-03-03 |  |  | 10 |  |  | 7 | 22.4003 | LSGL6335Z |  | Y | N | 048231348959 | Y | 0.0 |  | 40 |  |  |  |  | 3: 40
79 | CVZ | Final Assembly | C11 | 6C1X02KP | LSGL6335Z | ABDELCA | LSGL6335Z.ABDELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 11:22 | 2026-03-03 11:42 | 2026-03-03 |  |  | 10 |  |  | 7 | 22.4003 | LSGL6335Z |  | Y | N | 048231348959 | Y | 0.0 |  | 40 |  |  |  |  | 3: 40
80 | CVZ | Final Assembly | C11 | 6C1X02DR | LSDS6338F | ARSLSTD | LSDS6338F.ARSLSTD |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 11:42 | 2026-03-03 11:54 | 2026-03-03 |  |  | 10 |  |  | 7 | 18.9567 | LSDS6338F |  | Y | N | 195174020579 | Y | 0.0 |  | 24 |  |  |  |  | 3: 24
81 | CVZ | Final Assembly | C11 | 6C1X02D8 | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 11:54 | 2026-03-03 13:06 | 2026-03-03 |  |  | 10 |  |  | 7 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 24 |  |  |  |  | 3: 24
82 | CVZ | Final Assembly | C11 | 6C1X02KQ | LTEL7337F | ARSLLGA | LTEL7337F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 13:06 | 2026-03-03 13:16 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.3987 | LTEL7337F |  | Y | N | 048231344067 | Y | 0.0 |  | 20 |  |  |  |  | 3: 20
83 | CVZ | Final Assembly | C11 | 6C1X023T | LSIS6338NE | AEHLSTC | LSIS6338NE.AEHLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 13:16 | 2026-03-03 13:28 | 2026-03-03 |  |  | 10 |  |  | 7 | 17.8073 | LSIS6338NE |  | Y | N | 195174084427 | Y | 0.0 |  | 24 |  |  |  |  | 3: 24
84 | CVZ | Final Assembly | C11 | 6C1X02GP | LSIS6338NE | AEHLSTC | LSIS6338NE.AEHLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 13:28 | 2026-03-03 13:46 | 2026-03-03 |  |  | 10 |  |  | 7 | 17.8073 | LSIS6338NE |  | Y | N | 195174084427 | Y | 0.0 |  | 36 |  |  |  |  | 3: 36
85 | CVZ | Final Assembly | C11 | 6C1X02LY | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 13:46 | 2026-03-03 13:51 | 2026-03-03 |  |  | 10 |  |  | 7 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 10 |  |  |  |  | 3: 10
86 | CVZ | Final Assembly | C11 | 6C1X023S | LSIS6338F | AR1LSTC | LSIS6338F.AR1LSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 13:51 | 2026-03-03 14:01 | 2026-03-03 |  |  | 10 |  |  | 7 | 17.732 | LSIS6338F |  | Y | N | 195174020562 | Y | 0.0 |  | 20 |  |  |  |  | 3: 20
87 | CVZ | Final Assembly | C11 | 6C1X023B | LSES6338F | ARSLSTC | LSES6338F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 14:01 | 2026-03-03 14:03 | 2026-03-03 |  |  | 10 |  |  | 7 | 16.5455 | LSES6338F |  | Y | N | 195174035528 | Y | 0.0 |  | 5 |  |  |  |  | 3: 5
88 | CVZ | Final Assembly | C11 | 6C1X02EB | LSES6338F | ARSLSTC | LSES6338F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 14:03 | 2026-03-03 14:08 | 2026-03-03 |  |  | 10 |  |  | 7 | 16.5455 | LSES6338F |  | Y | N | 195174035528 | Y | 0.0 |  | 10 |  |  |  |  | 3: 10
89 | CVZ | Final Assembly | C11 | 6C1X02GM | LSES6338F | ARSLSTD | LSES6338F.ARSLSTD |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 14:08 | 2026-03-03 14:22 | 2026-03-03 |  |  | 10 |  |  | 7 | 15.9684 | LSES6338F |  | Y | N | 195174020593 | Y | 0.0 |  | 28 |  |  |  |  | 3: 28
90 | CVZ | Final Assembly | C11 | 6C1X02MK | WDEP9427F | ARSLLGA | WDEP9427F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 14:22 | 2026-03-03 14:25 | 2026-03-03 |  |  | 10 |  |  | 7 | 42.0463 | WDEP9427F |  | Y | N | 048231344289 | Y | 0.0 |  | 5 |  |  |  |  | 3: 5
91 | CVZ | Final Assembly | C11 | 6C1X02HG | WDEP9423D | ABDLLGA | WDEP9423D.ABDLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 14:25 | 2026-03-03 14:27 | 2026-03-03 |  |  | 10 |  |  | 7 | 40.2495 | WDEP9423D |  | Y | N | 048231344807 | Y | 0.0 |  | 4 |  |  |  |  | 3: 4
92 | CVZ | Final Assembly | C11 | 6C1X02GR | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-03 14:27 | 2026-03-03 14:43 | 2026-03-03 |  |  | 10 |  |  | 7 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 32 |  |  |  |  | 3: 32
93 | CVZ | Final Assembly | C11 | 6C1X02GQ | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 14:43 | 2026-03-03 15:24 | 2026-03-03 |  |  | 10 |  |  | 7 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 63 |  |  |  |  | 3: 63
94 | CVZ | Final Assembly | C11 | 6C1X02HF | WDEK9419S | ASTLSGN | WDEK9419S.ASTLSGN |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-03 15:24 | 2026-03-03 15:26 | 2026-03-03 |  |  | 10 |  |  | 7 | 41.0459 | SKSDV3002S |  | Y | N | 048231341288 | Y | 0.0 |  | 3 |  |  |  |  | 3: 3
95 | CVZ | Final Assembly | C11 | 6C1X02DB | WDEK9419S | ASTLSGN | WDEK9419S.ASTLSGN |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 15:26 | 2026-03-03 15:29 | 2026-03-03 |  |  | 10 |  |  | 7 | 41.0459 | SKSDV3002S |  | Y | N | 048231341288 | Y | 0.0 |  | 7 |  |  |  |  | 3: 7
96 | CVZ | Final Assembly | C11 | 6C1X0245 | WSEP4727F | ARSLLCA | WSEP4727F.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 15:29 | 2026-03-03 15:34 | 2026-03-03 |  |  | 10 |  |  | 7 | 21.3974 | WSEP4727F |  | Y | N | 048231344302 | Y | 0.0 |  | 9 |  |  |  |  | 3: 9
97 | CVZ | Final Assembly | C11 | 6C1X02KV | WSEP4727F | ARSLLGA | WSEP4727F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 15:34 | 2026-03-03 15:47 | 2026-03-03 |  |  | 10 |  |  | 7 | 21.3974 | WSEP4727F |  | Y | N | 048231344302 | Y | 0.0 |  | 27 |  |  |  |  | 3: 27
98 | CVZ | Final Assembly | C11 | 6C1X02DX | WSEP4723D | ABDLLGA | WSEP4723D.ABDLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 15:47 | 2026-03-03 16:19 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.0724 | WSEP4723D |  | Y | N | 048231344784 | Y | 0.0 |  | 63 |  |  |  |  | 3: 63
99 | CVZ | Final Assembly | C11 | 6C1X02DD | WSEP4723D | ABDLLGA | WSEP4723D.ABDLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-03 16:19 | 2026-03-03 16:55 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.0724 | WSEP4723D |  | Y | N | 048231344784 | Y | 0.0 |  | 72 |  |  |  |  | 3: 72
100 | CVZ | Final Assembly | C11 | 6C1X02EJ | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-03 16:55 | 2026-03-03 17:56 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 63 |  |  |  |  | 3: 63
101 | CVZ | Final Assembly | C11 | 6C1X02HL | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-03-03 17:56 | 2026-03-03 18:28 | 2026-03-09 |  |  | 10 |  |  | 13 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 63 |  |  |  |  | 3: 63
102 | CVZ | Final Assembly | C11 | 6C1X02M3 | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-03 18:28 | 2026-03-03 19:20 | 2026-03-03 |  |  | 10 |  |  | 7 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 104 |  |  |  |  | 3: 104
103 | CVZ | Final Assembly | C11 | 6C1X02HN | WSES4728F | ARSLSTC | WSES4728F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 19:20 | 2026-03-03 19:22 | 2026-03-03 |  |  | 10 |  |  | 7 | 21.4115 | WSES4728F |  | Y | N | 195174022849 | Y | 0.0 |  | 4 |  |  |  |  | 3: 4
104 | CVZ | Final Assembly | C11 | 6C1X0246 | WSES4728F | ARSLSTC | WSES4728F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-03 19:22 | 2026-03-03 19:30 | 2026-03-03 |  |  | 10 |  |  | 7 | 21.4115 | WSES4728F |  | Y | N | 195174022849 | Y | 0.0 |  | 16 |  |  |  |  | 3: 16
105 | CVZ | Final Assembly | C11 | 6CMGV00G | WSED3023B | ABKLLNA | WSED3023B.ABKLLNA |  |  |  |  | MG |  |  |  | DM | 2026-03-03 19:30 | 2026-03-04 08:05 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.6353 | WSED3023B |  | Y | N | 195174071458 | Y |  |  | 10 |  |  |  |  | 3: 1; 4: 9
106 | CVZ | Final Assembly | C11 | 6C1X02KS | WSED3023B | ABKLLNA | WSED3023B.ABKLLNA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-04 08:05 | 2026-03-04 08:08 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.6353 | WSED3023B |  | Y | N | 195174071458 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
107 | CVZ | Final Assembly | C11 | 6C1X02BC | WSED3023B | ABKLLNA | WSED3023B.ABKLLNA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-04 08:08 | 2026-03-04 08:12 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.6353 | WSED3023B |  | Y | N | 195174071458 | Y | 0.0 |  | 9 |  |  |  |  | 4: 9
108 | CVZ | Final Assembly | C11 | 6C1X02ML | WSED3023B | ABKLLNA | WSED3023B.ABKLLNA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-04 08:12 | 2026-03-04 08:21 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.6353 | WSED3023B |  | Y | N | 195174071458 | Y | 0.0 |  | 18 |  |  |  |  | 4: 18
109 | CVZ | Final Assembly | C11 | 6CMGV00M | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 08:21 | 2026-03-04 08:23 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y |  |  | 4 |  |  |  |  | 4: 4
110 | CVZ | Final Assembly | C11 | 6C1X02JF | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-04 08:23 | 2026-03-04 08:26 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
111 | CVZ | Final Assembly | C11 | 6C1X02FT | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-04 08:26 | 2026-03-04 08:30 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 7 |  |  |  |  | 4: 7
112 | CVZ | Final Assembly | C11 | 6C1X02C3 | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | VMI NJ | USSE000023 | 2026-03-04 08:30 | 2026-03-04 08:34 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 8 |  |  |  |  | 4: 8
113 | CVZ | Final Assembly | C11 | 6C1X02EZ | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | VMI TX | USSE000022 | 2026-03-04 08:34 | 2026-03-04 08:38 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 8 |  |  |  |  | 4: 8
114 | CVZ | Final Assembly | C11 | 6C1X02FJ | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-04 08:38 | 2026-03-04 08:42 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 8 |  |  |  |  | 4: 8
115 | CVZ | Final Assembly | C11 | 6C1X02BL | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-04 08:42 | 2026-03-04 08:47 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 11 |  |  |  |  | 4: 11
116 | CVZ | Final Assembly | C11 | 6C1X02LN | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-03-04 08:47 | 2026-03-04 08:53 | 2026-03-16 |  |  | 10 |  |  | 20 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 11 |  |  |  |  | 4: 11
117 | CVZ | Final Assembly | C11 | 6C1X02CN | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-04 08:53 | 2026-03-04 09:01 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 17 |  |  |  |  | 4: 17
118 | CVZ | Final Assembly | C11 | 6C1X02EY | WCEP6427F | ARSLLGA | WCEP6427F.ARSLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-04 09:01 | 2026-03-04 09:10 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9323 | WCEP6427F |  | Y | N | 048231344326 | Y | 0.0 |  | 18 |  |  |  |  | 4: 18
119 | CVZ | Final Assembly | C11 | 6CMGV00V | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 09:10 | 2026-03-04 09:13 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y |  |  | 6 |  |  |  |  | 4: 6
120 | CVZ | Final Assembly | C11 | 6C1X02C8 | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-04 09:13 | 2026-03-04 09:16 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
121 | CVZ | Final Assembly | C11 | 6C1X02C9 | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-04 09:16 | 2026-03-04 09:19 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
122 | CVZ | Final Assembly | C11 | 6C1X02JZ | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION POR | USSE000047 | 2026-03-04 09:19 | 2026-03-04 09:22 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
123 | CVZ | Final Assembly | C11 | 6C1X02K9 | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-04 09:22 | 2026-03-04 09:26 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y | 0.0 |  | 8 |  |  |  |  | 4: 8
124 | CVZ | Final Assembly | C11 | 6C1X02FS | WCEP6423F | ARSLLGA | WCEP6423F.ARSLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-04 09:26 | 2026-03-04 09:33 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.7255 | WCEP6423F |  | Y | N | 048231344753 | Y | 0.0 |  | 13 |  |  |  |  | 4: 13
125 | CVZ | Final Assembly | C11 | 6CMGV00D | WCEK6419S | ASTLSGN | WCEK6419S.ASTLSGN |  |  |  |  | MG |  |  |  | DM | 2026-03-04 09:33 | 2026-03-04 09:35 | 2026-03-10 |  |  | 10 |  |  | 14 | 21.0215 | SKSCV3002S |  | Y | N | 048231341295 | Y |  |  | 5 |  |  |  |  | 4: 5
126 | CVZ | Final Assembly | C11 | 6C1X01KV | LDEL7324SE | ASTLLCA | LDEL7324SE.ASTLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 09:35 | 2026-03-04 09:53 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.7723 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 35 |  |  |  |  | 4: 35
127 | CVZ | Final Assembly | C11 | 6CMGV009 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 09:53 | 2026-03-04 09:57 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y |  |  | 8 |  |  |  |  | 4: 8
128 | CVZ | Final Assembly | C11 | 6C1X02CU | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | VMI OR | USSE000005 | 2026-03-04 09:57 | 2026-03-04 09:59 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 5 |  |  |  |  | 4: 5
129 | CVZ | Final Assembly | C11 | 6C1X02JT | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | VMI TX | USSE000022 | 2026-03-04 09:59 | 2026-03-04 10:12 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
130 | CVZ | Final Assembly | C11 | 6C1X02J1 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-04 10:12 | 2026-03-04 10:17 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 9 |  |  |  |  | 4: 9
131 | CVZ | Final Assembly | C11 | 6C1X02EP | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-04 10:17 | 2026-03-04 10:22 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 10 |  |  |  |  | 4: 10
132 | CVZ | Final Assembly | C11 | 6C1X02G4 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-04 10:22 | 2026-03-04 10:27 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 10 |  |  |  |  | 4: 10
133 | CVZ | Final Assembly | C11 | 6C1X02JU | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | VMI NJ | USSE000023 | 2026-03-04 10:27 | 2026-03-04 10:32 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 10 |  |  |  |  | 4: 10
134 | CVZ | Final Assembly | C11 | 6C1X02FP | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION OFL | USSE000046 | 2026-03-04 10:32 | 2026-03-04 10:37 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 11 |  |  |  |  | 4: 11
135 | CVZ | Final Assembly | C11 | 6C1X02L2 | LDEL7324SE | ASTLLGA | LDEL7324SE.ASTLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-04 10:37 | 2026-03-04 10:43 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.2794 | LDEL7324SE |  | Y | N | 048231347297 | Y | 0.0 |  | 12 |  |  |  |  | 4: 12
136 | CVZ | Final Assembly | C11 | 6C1X02E9 | FZ474PGV | AS2LLGA | FZ474PGV.AS2LLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-04 10:43 | 2026-03-04 10:45 | 2026-03-03 |  |  | 10 |  |  | 7 | 26.0362 | LUTD4919SN |  | Y | N | 048232335408 | Y | 0.0 |  | 4 |  |  |  |  | 4: 4
137 | CVZ | Final Assembly | C11 | 6CMGV005 | FZ474PGV | AS2LLGA | FZ474PGV.AS2LLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 10:45 | 2026-03-04 10:48 | 2026-03-10 |  |  | 10 |  |  | 14 | 26.0362 | LUTD4919SN |  | Y | N | 048232335408 | Y |  |  | 5 |  |  |  |  | 4: 5
138 | CVZ | Final Assembly | C11 | 6C1X029D | LSGS6338N | AEHESTC | LSGS6338N.AEHESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 10:48 | 2026-03-04 10:49 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.882 | LSGS6338N |  | Y | N | 195174070031 | Y | 0.0 |  | 3 |  |  |  |  | 4: 3
139 | CVZ | Final Assembly | C11 | 6C1X02MJ | LSGS6338N | AEHESTC | LSGS6338N.AEHESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 10:49 | 2026-03-04 10:53 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.882 | LSGS6338N |  | Y | N | 195174070031 | Y | 0.0 |  | 7 |  |  |  |  | 4: 7
140 | CVZ | Final Assembly | C11 | 6C1X028J | LSGS6338F | ARSESTC | LSGS6338F.ARSESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 10:53 | 2026-03-04 10:55 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9165 | LSGS6338F |  | Y | N | 195174035535 | Y | 0.0 |  | 5 |  |  |  |  | 4: 5
141 | CVZ | Final Assembly | C11 | 6C1X02HE | LSGS6338F | ARSESTC | LSGS6338F.ARSESTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 10:55 | 2026-03-04 11:03 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9165 | LSGS6338F |  | Y | N | 195174035535 | Y | 0.0 |  | 15 |  |  |  |  | 4: 15
142 | CVZ | Final Assembly | C11 | 6CMGV001 | LSGS6338F | ARSESTD | LSGS6338F.ARSESTD |  |  |  |  | MG |  |  |  | DM | 2026-03-04 11:03 | 2026-03-04 11:17 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.9165 | LSGS6338F |  | Y | N | 195174020722 | Y |  |  | 29 |  |  |  |  | 4: 29
143 | CVZ | Final Assembly | C11 | 6C1X01L2 | LSGL6335X | ARSELCA | LSGL6335X.ARSELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 11:17 | 2026-03-04 11:35 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.4038 | LSGL6335X |  | Y | N | 048231348942 | Y | 0.0 |  | 36 |  |  |  |  | 4: 36
144 | CVZ | Final Assembly | C11 | 6C1X02GN | LSGL6335X | ARSELCA | LSGL6335X.ARSELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 11:35 | 2026-03-04 13:16 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.4038 | LSGL6335X |  | Y | N | 048231348942 | Y | 0.0 |  | 82 |  |  |  |  | 4: 82
145 | CVZ | Final Assembly | C11 | 6C1X02LX | LSGL6335X | ARSELCA | LSGL6335X.ARSELCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 13:16 | 2026-03-04 14:40 | 2026-03-10 |  |  | 10 |  |  | 14 | 19.4038 | LSGL6335X |  | Y | N | 048231348942 | Y | 0.0 |  | 168 |  |  |  |  | 4: 168
146 | CVZ | Final Assembly | C11 | 6CMGV00H | LSDS6338F | ARSLSTD | LSDS6338F.ARSLSTD |  |  |  |  | MG |  |  |  | DM | 2026-03-04 14:40 | 2026-03-04 14:46 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.9567 | LSDS6338F |  | Y | N | 195174020579 | Y |  |  | 12 |  |  |  |  | 4: 12
147 | CVZ | Final Assembly | C11 | 6CMGV011 | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 14:46 | 2026-03-04 14:53 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y |  |  | 13 |  |  |  |  | 4: 13
148 | CVZ | Final Assembly | C11 | 6C1X02LH | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | VMI TX | USSE000022 | 2026-03-04 14:53 | 2026-03-04 14:55 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 5 |  |  |  |  | 4: 5
149 | CVZ | Final Assembly | C11 | 6C1X02K4 | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-04 14:55 | 2026-03-04 14:58 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 6 |  |  |  |  | 4: 6
150 | CVZ | Final Assembly | C11 | 6C1X02HV | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-04 14:58 | 2026-03-04 15:12 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 7 |  |  |  |  | 4: 7
151 | CVZ | Final Assembly | C11 | 6C1X02JV | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | VMI OR | USSE000005 | 2026-03-04 15:12 | 2026-03-04 15:16 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 8 |  |  |  |  | 4: 8
152 | CVZ | Final Assembly | C11 | 6C1X02LG | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-04 15:16 | 2026-03-04 15:20 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 9 |  |  |  |  | 4: 9
153 | CVZ | Final Assembly | C11 | 6C1X02CJ | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | VMI NJ | USSE000023 | 2026-03-04 15:20 | 2026-03-04 15:27 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 13 |  |  |  |  | 4: 13
154 | CVZ | Final Assembly | C11 | 6C1X02KY | LSDL6336F | ARSLLGA | LSDL6336F.ARSLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-04 15:27 | 2026-03-04 15:34 | 2026-03-10 |  |  | 10 |  |  | 14 | 18.0175 | LSDL6336F |  | Y | N | 048231342629 | Y | 0.0 |  | 14 |  |  |  |  | 4: 14
155 | CVZ | Final Assembly | C11 | 6CMGV00B | LTEL7337F | ARSLLGA | LTEL7337F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-04 15:34 | 2026-03-04 15:47 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.3987 | LTEL7337F |  | Y | N | 048231344067 | Y |  |  | 27 |  |  |  |  | 4: 27
156 | CVZ | Final Assembly | C11 | 6C1X01L6 | LSIL6332FE | ARSLLCA | LSIL6332FE.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 15:47 | 2026-03-04 19:22 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.745 | LSIL6332FE |  | Y | N | 195174080702 | Y | 0.0 |  | 370 |  |  |  |  | 4: 370
157 | CVZ | Final Assembly | C11 | 6C1X01L1 | LSES6338F | ARSLSTC | LSES6338F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 19:22 | 2026-03-04 19:27 | 2026-03-10 |  |  | 10 |  |  | 14 | 16.5455 | LSES6338F |  | Y | N | 195174035528 | Y | 0.0 |  | 10 |  |  |  |  | 4: 10
158 | CVZ | Final Assembly | C11 | 6C1X0289 | LSEL6335ZE | ABDLLCA | LSEL6335ZE.ABDLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-04 19:27 | 2026-03-05 08:27 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.0297 | LSEL6335ZE |  | Y | N | 048231348973 | Y | 0.0 |  | 60 |  |  |  |  | 4: 6; 5: 54
159 | CVZ | Final Assembly | C11 | 6C1X02DS | LSEL6335ZE | ABDLLCA | LSEL6335ZE.ABDLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-05 08:27 | 2026-03-05 09:09 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.0297 | LSEL6335ZE |  | Y | N | 048231348973 | Y | 0.0 |  | 84 |  |  |  |  | 5: 84
160 | CVZ | Final Assembly | C11 | 6C1X02KN | LSEL6335ZE | ABDLLCA | LSEL6335ZE.ABDLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-05 09:09 | 2026-03-05 10:12 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.0297 | LSEL6335ZE |  | Y | N | 048231348973 | Y | 0.0 |  | 106 |  |  |  |  | 5: 106
161 | CVZ | Final Assembly | C11 | 6C1X029S | WSED7612S | ASTQEUN | WSED7612S.ASTQEUN |  |  |  |  | FO |  |  | LGESW | SE001021A1 | 2026-03-05 10:12 | 2026-03-05 10:32 | 2026-03-05 |  |  | 10 |  |  | 9 | 14.9435 | WSED7612S |  | Y | N | 8806096438435 | Y | 0.0 |  | 40 |  |  |  |  | 5: 40
162 | CVZ | Final Assembly | C11 | 6C1X02PP | WSED7612S | ASTQEUN | WSED7612S.ASTQEUN |  |  |  |  | FO |  |  | NSI Electronic Aps/ DD | DK001741A1 | 2026-03-05 10:32 | 2026-03-05 11:26 | 2026-03-09 |  |  | 10 |  |  | 13 | 14.9435 | WSED7612S |  | Y | N | 8806096438435 | Y | 0.0 |  | 108 |  |  |  |  | 5: 108
163 | CVZ | Final Assembly | C11 | 6C1X029T | WSED7612S | ASTQEUR | WSED7612S.ASTQEUR |  |  |  |  | FO |  |  | LGEES | ES001013A1 | 2026-03-05 11:26 | 2026-03-05 14:34 | 2026-03-05 |  |  | 10 |  |  | 9 | 14.9435 | WSED7612S |  | Y | N | 8806091858160 | Y | 0.0 |  | 256 |  |  |  |  | 5: 256
164 | CVZ | Final Assembly | C11 | 6C1X028F | WSED7613S | ASTQEUR | WSED7613S.ASTQEUR |  |  |  |  | FO |  |  | LGEES | ES001013A1 | 2026-03-05 14:34 | 2026-03-05 14:57 | 2026-03-05 |  |  | 10 |  |  | 9 | 14.9435 | WSED7613S |  | Y | N | 8806091858139 | Y | 0.0 |  | 45 |  |  |  |  | 5: 45
165 | CVZ | Final Assembly | C11 | 6BSYV007 | LSGU6339X | BRSLDV1 | LSGU6339X.BRSLDV1 |  |  |  |  | SY |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-03-05 14:57 | 2026-03-05 15:14 | 2026-02-20 | 2026-02-21 |  | 10 | 51 | 52 | -4 | 20.9165 |  |  | Y | N | 195174135921 | N | 3/6일변경(신뢰성이슈)2/21변경(인정시험 capa부족으로 인한 시험 지연),2/13일 요청, PV제작_LG 2nd SIGNATURE_ 박형종A |  | 15 |  |  |  |  | 5: 15
166 | CVZ | Final Assembly | C11 | 6CSYV003 | LSGU6339X | BRSLPV1 | LSGU6339X.BRSLPV1 |  |  | Y |  | SY |  |  | BEST BUY PURCHASING LLC | US015530A4 | 2026-03-05 15:14 | 2026-03-05 15:22 | 2026-03-19 |  |  | 10 |  |  | 23 | 22.0312 |  |  | Y | N | 195174151020 | N | 3/6일변경(신뢰성이슈)2/21변경(인정시험 capa부족으로 인한 시험 지연),2/13일 요청, PV제작_LG 2nd SIGNATURE_ 박형종A |  | 15 |  |  |  |  | 5: 15
167 | CVZ | Final Assembly | C11 | 6CMGV00F | LSES6338F | ARSLSTD | LSES6338F.ARSLSTD |  |  |  |  | MG |  |  |  | DM | 2026-03-05 15:22 | 2026-03-05 15:27 | 2026-03-10 |  |  | 10 |  |  | 14 | 15.9684 | LSES6338F |  | Y | N | 195174020593 | Y |  |  | 11 |  |  |  |  | 5: 11
168 | CVZ | Final Assembly | C11 | 6CMGV00W | WDEP9427F | ARSLLGA | WDEP9427F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 15:27 | 2026-03-05 15:35 | 2026-03-10 |  |  | 10 |  |  | 14 | 42.0463 | WDEP9427F |  | Y | N | 048231344289 | Y |  |  | 16 |  |  |  |  | 5: 16
169 | CVZ | Final Assembly | C11 | 6CMGV004 | WDEP9423D | ABDLLGA | WDEP9423D.ABDLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 15:35 | 2026-03-05 15:48 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.2495 | WDEP9423D |  | Y | N | 048231344807 | Y |  |  | 25 |  |  |  |  | 5: 25
170 | CVZ | Final Assembly | C11 | 6CMGV008 | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 15:48 | 2026-03-05 15:50 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y |  |  | 5 |  |  |  |  | 5: 5
171 | CVZ | Final Assembly | C11 | 6C1X02JB | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-05 15:50 | 2026-03-05 15:53 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 6 |  |  |  |  | 5: 6
172 | CVZ | Final Assembly | C11 | 6C1X02FV | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION OFL | USSE000046 | 2026-03-05 15:53 | 2026-03-05 15:57 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 7 |  |  |  |  | 5: 7
173 | CVZ | Final Assembly | C11 | 6C1X02CD | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-05 15:57 | 2026-03-05 16:01 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 8 |  |  |  |  | 5: 8
174 | CVZ | Final Assembly | C11 | 6C1X02CQ | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-05 16:01 | 2026-03-05 16:05 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 8 |  |  |  |  | 5: 8
175 | CVZ | Final Assembly | C11 | 6C1X02CT | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION FTW | USSE000044 | 2026-03-05 16:05 | 2026-03-05 16:09 | 2026-03-16 |  |  | 10 |  |  | 20 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 9 |  |  |  |  | 5: 9
176 | CVZ | Final Assembly | C11 | 6C1X02BN | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-05 16:09 | 2026-03-05 16:15 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 11 |  |  |  |  | 5: 11
177 | CVZ | Final Assembly | C11 | 6C1X02F1 | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | VMI NJ | USSE000023 | 2026-03-05 16:15 | 2026-03-05 16:20 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 11 |  |  |  |  | 5: 11
178 | CVZ | Final Assembly | C11 | 6C1X02J5 | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-05 16:20 | 2026-03-05 16:26 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 12 |  |  |  |  | 5: 12
179 | CVZ | Final Assembly | C11 | 6C1X02EM | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | VMI TX | USSE000022 | 2026-03-05 16:26 | 2026-03-05 16:34 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 16 |  |  |  |  | 5: 16
180 | CVZ | Final Assembly | C11 | 6C1X02L5 | WDEP9423F | ARSLLGA | WDEP9423F.ARSLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-05 16:34 | 2026-03-05 16:47 | 2026-03-10 |  |  | 10 |  |  | 14 | 40.3296 | WDEP9423F |  | Y | N | 048231344791 | Y | 0.0 |  | 26 |  |  |  |  | 5: 26
181 | CVZ | Final Assembly | C11 | 6CMGV00Z | WDES9428F | ARSLSTD | WDES9428F.ARSLSTD |  |  |  |  | MG |  |  |  | DM | 2026-03-05 16:47 | 2026-03-05 16:52 | 2026-03-10 |  |  | 10 |  |  | 14 | 41.2841 | WDES9428F |  | Y | N | 195174022825 | Y |  |  | 10 |  |  |  |  | 5: 10
182 | CVZ | Final Assembly | C11 | 6CMGV006 | LD3661SP | AS2LSGN | LD3661SP.AS2LSGN |  |  |  |  | MG |  |  |  | DM | 2026-03-05 16:52 | 2026-03-05 16:55 | 2026-03-10 |  |  | 10 |  |  | 14 | 36.7689 | UPWD3034ST |  | Y | N | 048231319706 | Y |  |  | 6 |  |  |  |  | 5: 6
183 | CVZ | Final Assembly | C11 | 6CMGV00R | WDEK9419S | ASTLSGN | WDEK9419S.ASTLSGN |  |  |  |  | MG |  |  |  | DM | 2026-03-05 16:55 | 2026-03-05 17:30 | 2026-03-10 |  |  | 10 |  |  | 14 | 41.0459 | SKSDV3002S |  | Y | N | 048231341288 | Y |  |  | 10 |  |  |  |  | 5: 10
184 | CVZ | Final Assembly | C11 | 6C1X01LS | WSEP4727F | ARSLLCA | WSEP4727F.ARSLLCA |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-05 17:30 | 2026-03-05 17:32 | 2026-03-10 |  |  | 10 |  |  | 14 | 21.3974 | WSEP4727F |  | Y | N | 048231344302 | Y | 0.0 |  | 3 |  |  |  |  | 5: 3
185 | CVZ | Final Assembly | C11 | 6CMGV00C | WSEP4727F | ARSLLGA | WSEP4727F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 17:32 | 2026-03-05 17:41 | 2026-03-10 |  |  | 10 |  |  | 14 | 21.3974 | WSEP4727F |  | Y | N | 048231344302 | Y |  |  | 19 |  |  |  |  | 5: 19
186 | CVZ | Final Assembly | C11 | 6CMGV00N | WSEP4723D | ABDLLGA | WSEP4723D.ABDLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 17:41 | 2026-03-05 17:51 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723D |  | Y | N | 048231344784 | Y |  |  | 20 |  |  |  |  | 5: 20
187 | CVZ | Final Assembly | C11 | 6C1X02MM | WSEP4723D | ABDLLGA | WSEP4723D.ABDLLGA |  |  |  |  | FO |  |  | NCR PSI LOCATION | USSE000051 | 2026-03-05 17:51 | 2026-03-05 17:58 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723D |  | Y | N | 048231344784 | Y | 0.0 |  | 13 |  |  |  |  | 5: 13
188 | CVZ | Final Assembly | C11 | 6CMGV00J | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | MG |  |  |  | DM | 2026-03-05 17:58 | 2026-03-05 18:01 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y |  |  | 6 |  |  |  |  | 5: 6
189 | CVZ | Final Assembly | C11 | 6C1X02GU | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | VMI OR | USSE000005 | 2026-03-05 18:01 | 2026-03-05 18:03 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 5 |  |  |  |  | 5: 5
190 | CVZ | Final Assembly | C11 | 6C1X02CC | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-05 18:03 | 2026-03-05 18:06 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 5 |  |  |  |  | 5: 5
191 | CVZ | Final Assembly | C11 | 6C1X02EH | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | VMI IL | USSE000036 | 2026-03-05 18:06 | 2026-03-05 18:09 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 7 |  |  |  |  | 5: 7
192 | CVZ | Final Assembly | C11 | 6C1X02DY | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | PKD | USSE000049 | 2026-03-05 18:09 | 2026-03-05 18:14 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 9 |  |  |  |  | 5: 9
193 | CVZ | Final Assembly | C11 | 6C1X02MN | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | LGEUS LOCATION OFL | USSE000046 | 2026-03-05 18:14 | 2026-03-05 18:20 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 12 |  |  |  |  | 5: 12
194 | CVZ | Final Assembly | C11 | 6C1X02HK | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | VMI NJ | USSE000023 | 2026-03-05 18:20 | 2026-03-05 18:26 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 13 |  |  |  |  | 5: 13
195 | CVZ | Final Assembly | C11 | 6C1X02CR | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | LG GA WHSE | USSE000055 | 2026-03-05 18:26 | 2026-03-05 18:34 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 16 |  |  |  |  | 5: 16
196 | CVZ | Final Assembly | C11 | 6C1X02KZ | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | VMI TX | USSE000022 | 2026-03-05 18:34 | 2026-03-05 18:42 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 16 |  |  |  |  | 5: 16
197 | CVZ | Final Assembly | C11 | 6C1X02DE | WSEP4723F | ARSLLGA | WSEP4723F.ARSLLGA |  |  |  |  | FO |  |  | VMI CA | USSE000007 | 2026-03-05 18:42 | 2026-03-05 18:52 | 2026-03-10 |  |  | 10 |  |  | 14 | 20.0724 | WSEP4723F |  | Y | N | 048231344777 | Y | 0.0 |  | 19 |  |  |  |  | 5: 19
198 | CVZ | Final Assembly | C11 | 6C1X01LT | WSES4728F | ARSLSTC | WSES4728F.ARSLSTC |  |  |  |  | FO |  |  | LGECI | CA001024A1 | 2026-03-05 18:52 | 2026-03-05 18:56 | 2026-03-10 |  |  | 10 |  |  | 14 | 21.4115 | WSES4728F |  | Y | N | 195174022849 | Y | 0.0 |  | 8 |  |  |  |  | 5: 8
199 | CVZ | Final Assembly | C11 | 6B1X00YX | LTGL6937F | AR1ELGA | LTGL6937F.AR1ELGA |  |  |  |  | FO |  |  | CFN | USSE000052 | 2026-03-05 18:56 | 2026-03-06 13:16 | 2026-02-24 |  |  | 10 |  |  | 0 | 25.5953 | LTGL6937F |  | Y | N | 048231344173 | Y | 3/12일 변경(시그니처 2세대 550대 대응으로 인한 공용자재 수급 이슈) |  | 560 |  |  |  |  | 5: 69